## Project Overview
Payroll Data Visualization – Project Overview
Project ID | VIZ-01
Project Title | Payroll Data Visualization & EDA
Domain | HR / Data Analytics
Type | Data Visualization Project
Duration | 15 Days (Sprint 1: Days 1–5 ¦ Sprint 2: Days 6–10 ¦ Sprint 3: Days 11–15)
Start Date | 21-04-2026
End Date | 05-05-2026
Tech Stack | Python, Pandas, Matplotlib, Seaborn, NumPy
Dataset | PAYROLL_CLEANED.xlsx (columns: TOTAL_PAY, GENDER, JOB_TITLE, DEPARTMENT_TITLE, EMPLOYMENT_TYPE, BENEFIT_PAY, OVERTIME_PAY, ETHNICITY)
Goal | Perform EDA and build 13 analytical visualizations on payroll data to uncover salary patterns, gender pay gaps, department-wise trends, employment-type comparisons, and key HR insights.

## Epics & Stories
Payroll Data Visualization – Epics, Stories & Tasks
Issue Key | Type | Epic / Story / Task | Description | Sprint | Priority | Story Points | Status | Start Date | Due Date
VIZ-E1 | EPIC | Project Setup & Data Loading | Set up Python environment, load PAYROLL_CLEANED.xlsx, validate schema, and perform basic data checks. | 1 | High | - | To Do | 21-04-2026 | 25-04-2026
VIZ-S1 | STORY | Environment Setup & Data Ingestion | As a data analyst, I want a working Python setup and loaded dataset so that analysis can begin. | 1 | High | 3 | To Do
VIZ-T1 | TASK | Create project folder structure (/data /notebooks /visuals /reports) | Organise working directory for reproducibility. | 1 | High | 1 | To Do
VIZ-T2 | TASK | Install and import libraries: Pandas, NumPy, Matplotlib, Seaborn | Verify all imports work; document versions in requirements.txt. | 1 | High | 1 | To Do
VIZ-T3 | TASK | Load PAYROLL_CLEANED.xlsx into Pandas DataFrame using pd.read_excel() | Print df.shape, df.head(), df.columns to confirm successful load. | 1 | High | 1 | To Do
VIZ-S2 | STORY | Schema Validation & Initial Exploration | As a data analyst, I want to validate column names, types, and basic stats before visualising. | 1 | High | 2 | To Do
VIZ-T4 | TASK | Run df.info() and df.dtypes – validate column names and data types | Check TOTAL_PAY, BENEFIT_PAY, OVERTIME_PAY are numeric; date/string columns are correct. | 1 | High | 1 | To Do
VIZ-T5 | TASK | Run df.isnull().sum() and df.duplicated().sum() – check data quality | Document any missing values or duplicate rows found. | 1 | Medium | 1 | To Do
VIZ-E2 | EPIC | Salary & Compensation Analysis Visualizations | Build charts that reveal salary distribution, compensation structure, and top-earning roles/departments. | 2 | High | - | To Do | 26-04-2026 | 30-04-2026
VIZ-S3 | STORY | Salary Distribution Analysis | As an HR analyst, I want to see how salaries are spread so I can identify normal ranges and outliers. | 2 | High | 4 | To Do
VIZ-T6 | TASK | Plot salary distribution – Histogram + KDE (TOTAL_PAY) | Use sns.histplot(df['TOTAL_PAY'], kde=True). Add title 'Salary Distribution'. Conclude: approximately normal distribution with mid-range majority. | 2 | High | 2 | To Do
VIZ-T7 | TASK | Plot Top 10 Job Titles by Average Salary – Bar chart | Group by JOB_TITLE, compute mean TOTAL_PAY, sort descending, plot top 10. Rotate x-labels 45°. | 2 | High | 2 | To Do
VIZ-S4 | STORY | Department & Employment Type Compensation | As an HR manager, I want department and employment-type salary comparisons to spot structural pay differences. | 2 | High | 4 | To Do
VIZ-T8 | TASK | Plot Average Salary by Department – Bar chart | Use sns.barplot(x='DEPARTMENT_TITLE', y='TOTAL_PAY'). Rotate x-labels 90°. Title: 'Average Salary by Department'. | 2 | High | 2 | To Do
VIZ-T9 | TASK | Plot Employment Type Distribution – Pie chart | Use df['EMPLOYMENT_TYPE'].value_counts().plot(kind='pie', autopct='%1.1f%%'). Title: 'Employment Type Distribution'. | 2 | Medium | 1 | To Do
VIZ-T10 | TASK | Plot Full-time vs Part-time Salary – Boxplot (EMPLOYMENT_TYPE vs TOTAL_PAY) | Use sns.boxplot(x='EMPLOYMENT_TYPE', y='TOTAL_PAY'). Title: 'Employment Type vs Salary'. | 2 | High | 1 | To Do
VIZ-T11 | TASK | Plot Highest Paying Dept per Employment Type – Grouped Bar / Pivot heatmap | pivot_table(values='TOTAL_PAY', index='DEPARTMENT_TITLE', columns='EMPLOYMENT_TYPE', aggfunc='mean').plot(kind='bar'). | 2 | High | 2 | To Do
VIZ-E3 | EPIC | Gender, Diversity & Equity Analysis | Examine gender-wise and ethnicity-wise pay patterns and overtime to surface DEI insights. | 2 | High | - | To Do | 26-04-2026 | 30-04-2026
VIZ-S5 | STORY | Gender Pay Analysis | As an HR analyst, I want to compare salaries and overtime pay by gender to identify potential pay gaps. | 2 | High | 4 | To Do
VIZ-T12 | TASK | Plot Gender vs Total Pay – Boxplot | sns.boxplot(x='GENDER', y='TOTAL_PAY'). Title: 'Gender vs Total Pay'. Conclude: median differences suggest role/experience-based disparity. | 2 | High | 2 | To Do
VIZ-T13 | TASK | Plot Gender vs Overtime Pay – Bar chart | sns.barplot(x='GENDER', y='OVERTIME_PAY'). Title: 'Gender vs Overtime Pay'. Identify which gender works more overtime on average. | 2 | High | 2 | To Do
VIZ-S6 | STORY | Diversity & Ethnicity Distribution | As an HR manager, I want to understand workforce ethnic composition for DEI reporting. | 2 | Medium | 2 | To Do
VIZ-T14 | TASK | Plot Employee Distribution by Ethnicity – Count plot | sns.countplot(x='ETHNICITY'). Rotate x-labels 45°. Title: 'Employee Distribution by Ethnicity'. | 2 | Medium | 2 | To Do
VIZ-E4 | EPIC | Benefits, Correlations & Role Frequency Analysis | Explore benefit pay vs total pay relationships, feature correlations, and most common job titles. | 3 | Medium | - | To Do | 01-05-2026 | 05-05-2026
VIZ-S7 | STORY | Benefits & Compensation Relationship | As a compensation analyst, I want to see how benefit pay relates to total pay to understand comp structure. | 3 | Medium | 3 | To Do
VIZ-T15 | TASK | Plot Benefit Pay vs Total Pay – Scatter plot | sns.scatterplot(x='BENEFIT_PAY', y='TOTAL_PAY'). Title: 'Benefit Pay vs Total Pay'. Observe positive linear trend. | 3 | Medium | 2 | To Do
VIZ-T16 | TASK | Plot Top 5 Highest Paid Employees by Job Title – Horizontal Bar chart | top5 = df.nlargest(5, 'TOTAL_PAY'). sns.barplot(x='TOTAL_PAY', y='JOB_TITLE', data=top5). Title: 'Top 5 Highest Paid Job Titles'. | 3 | High | 1 | To Do
VIZ-S8 | STORY | Correlation & Role Frequency Analysis | As a data analyst, I want a correlation heatmap and job title frequency chart to understand numeric relationships and workforce composition. | 3 | Medium | 4 | To Do
VIZ-T17 | TASK | Plot Correlation Matrix – Heatmap (all numeric features) | sns.heatmap(df.corr(numeric_only=True), annot=True). Title: 'Correlation Matrix'. Highlight strong relationships. | 3 | Medium | 2 | To Do
VIZ-T18 | TASK | Plot Top 10 Most Common Job Titles – Bar chart | df['JOB_TITLE'].value_counts().head(10).plot(kind='bar'). Rotate 45°. Title: 'Top 10 Most Common Job Titles'. | 3 | Medium | 2 | To Do
VIZ-E5 | EPIC | Insights Documentation & Final Submission | Write analysis conclusions for each chart, validate all 13 visualizations, and package final deliverables. | 3 | High | - | To Do | 01-05-2026 | 05-05-2026
VIZ-S9 | STORY | Conclusions & Narrative Writeup | As a project lead, I want written conclusions for every visualization so that HR stakeholders can act on findings. | 3 | High | 4 | To Do
VIZ-T19 | TASK | Write conclusion for each of the 13 visualizations (1–2 lines each) | E.g., Viz 1 → 'Normal distribution; most employees mid-range.' Viz 2 → 'Gender median gap – role-based not direct bias.' | 3 | High | 2 | To Do
VIZ-T20 | TASK | Validate all 13 charts render correctly without errors | Run full notebook top-to-bottom; fix any SettingWithCopyWarning or DeprecationWarning. | 3 | High | 1 | To Do
VIZ-S10 | STORY | Final Packaging & Submission | As a project lead, I want all deliverables packaged and submitted so the project is complete. | 3 | High | 3 | To Do
VIZ-T21 | TASK | Save all 13 charts as .png files to /visuals folder | Use plt.savefig('visuals/viz_01_salary_dist.png', dpi=150, bbox_inches='tight') for each chart. | 3 | High | 1 | To Do
VIZ-T22 | TASK | Write 1-page analysis summary report (key findings + recommendations) | Cover: salary range, gender gap, top departments, employment-type split, benefit-pay correlation. | 3 | High | 1 | To Do
VIZ-T23 | TASK | Submit final Jupyter Notebook (.ipynb) with all outputs visible | Ensure all cells executed, all plots inline, notebook saved with Kernel → Restart & Run All. | 3 | High | 1 | To Do

## Sprint Plan
Payroll Data Visualization – Sprint Plan (15 Days)
Sprint 1 – Days 1 to 5: Project Setup, Data Loading & Schema Validation (21-04-2026 to 25-04-2026)
Issue Key | Story / Task | Priority | Story Points | Status | Phase
VIZ-S1 | Environment Setup & Data Ingestion | High | 3 | To Do | Story
VIZ-T1 | Create project folder structure | High | 1 | To Do | Task
VIZ-T2 | Install and import libraries | High | 1 | To Do | Task
VIZ-T3 | Load PAYROLL_CLEANED.xlsx into DataFrame | High | 1 | To Do | Task
VIZ-S2 | Schema Validation & Initial Exploration | High | 2 | To Do | Story
VIZ-T4 | Run df.info() and df.dtypes | High | 1 | To Do | Task
VIZ-T5 | Run df.isnull().sum() and df.duplicated().sum() | Medium | 1 | To Do | Task
Sprint 2 – Days 6 to 10: Salary, Department, Gender & Diversity Charts (26-04-2026 to 30-04-2026)
Issue Key | Story / Task | Priority | Story Points | Status | Phase
VIZ-S3 | Salary Distribution Analysis | High | 4 | To Do | Story
VIZ-T6 | Salary Histogram + KDE | High | 2 | To Do | Task
VIZ-T7 | Top 10 Job Titles by Avg Salary – Bar chart | High | 2 | To Do | Task
VIZ-S4 | Department & Employment Type Compensation | High | 4 | To Do | Story
VIZ-T8 | Avg Salary by Department – Bar chart | High | 2 | To Do | Task
VIZ-T9 | Employment Type Distribution – Pie chart | Medium | 1 | To Do | Task
VIZ-T10 | Full-time vs Part-time Salary – Boxplot | High | 1 | To Do | Task
VIZ-T11 | Highest Paying Dept per Employment Type | High | 2 | To Do | Task
VIZ-S5 | Gender Pay Analysis | High | 4 | To Do | Story
VIZ-T12 | Gender vs Total Pay – Boxplot | High | 2 | To Do | Task
VIZ-T13 | Gender vs Overtime Pay – Bar chart | High | 2 | To Do | Task
VIZ-S6 | Diversity & Ethnicity Distribution | Medium | 2 | To Do | Story
VIZ-T14 | Employee Distribution by Ethnicity – Countplot | Medium | 2 | To Do | Task
Sprint 3 – Days 11 to 15: Benefits, Correlation, Insights & Submission (01-05-2026 to 05-05-2026)
Issue Key | Story / Task | Priority | Story Points | Status | Phase
VIZ-S7 | Benefits & Compensation Relationship | Medium | 3 | To Do | Story
VIZ-T15 | Benefit Pay vs Total Pay – Scatter plot | Medium | 2 | To Do | Task
VIZ-T16 | Top 5 Highest Paid Job Titles – Horizontal Bar | High | 1 | To Do | Task
VIZ-S8 | Correlation & Role Frequency Analysis | Medium | 4 | To Do | Story
VIZ-T17 | Correlation Matrix – Heatmap | Medium | 2 | To Do | Task
VIZ-T18 | Top 10 Most Common Job Titles – Bar chart | Medium | 2 | To Do | Task
VIZ-S9 | Conclusions & Narrative Writeup | High | 4 | To Do | Story
VIZ-T19 | Write conclusion for each of the 13 visualizations | High | 2 | To Do | Task
VIZ-T20 | Validate all 13 charts render correctly | High | 1 | To Do | Task
VIZ-S10 | Final Packaging & Submission | High | 3 | To Do | Story
VIZ-T21 | Save all 13 charts as .png to /visuals | High | 1 | To Do | Task
VIZ-T22 | Write 1-page analysis summary report | High | 1 | To Do | Task
VIZ-T23 | Submit final Jupyter Notebook (.ipynb) | High | 1 | To Do | Task